## Sheet1
Task | Start Date | Duration (Days)
Review module requirements | 2025-12-17 | 1
Research network programmability concepts | 2025-12-17 | 6
Learn automation tools (Ansible) | 2025-12-22 | 17
Analyse existing Cisco network setup | 2026-01-05 | 1
Design automation solution | 2026-01-05 | 11
Develop automation scripts | 2026-01-05 | 12
Test scripts on lab devices | 2026-01-10 | 5
Fix bugs and refine code | 2026-01-12 | 3
Produce documentation and report | 2026-01-15 | 3
Final submission | 2026-01-20 | 1